Kigali, 3 June 2026

To

His Honorable the Minister of Infrastructure (MININFRA)

And to

His Honorable the Minister of Finance and Economic Planning (MINECOFIN)

Subject: Request for Authorization to Recruit an Accredited Consultant and retender — KCSS Project

Your Honorables,

The Kigali Centralized Sewerage System (KCSS) is Rwanda's first centralized sewerage infrastructure at scale. This strategic project is financed by the European Investment Bank (EIB) and the African Development Bank (AfDB). It was awarded to CRCEG (China Railway Construction Engineering Group Co. Ltd), with CES Consulting Engineers as the supervision consultant. To date, the design has reached 90.6% completion; however, this was achieved after a cumulative delay of more than 30 months against an initial contractual design period of 6 months. Given the contractor's persistent failures — including failure to mobilize qualified staff, poor quality of deliverables, and inability to meet contractual obligations — WASAC Group formally notified the termination of the contract with CRCEG on 8 May 2026.

Following this termination, WASAC Group must take urgent action to safeguard the available financing, whose disbursement deadlines are set at 28 December 2027 for the EIB and 30 June 2028 for the AfDB.

It is important to highlight that this proposed approach was discussed with the African Development Bank team during their most recent supervision mission from 4 – 19 May 2026 and received a favourable assessment. The AfDB found the approach consistent with the financing timeline constraints and well-suited to the current stage of project design.

In this context, WASAC Group respectfully requests the authorization and endorsement of both Ministries for the following two-step approach:

First, to recruit a consultant accredited by the Ministry of Infrastructure (MININFRA) to review and validate the existing design (90.6% complete) and finalize the remaining 9.4%. This step is essential to obtain a certified and complete design package that will serve as the basis for the works tender.

Second, on the basis of the validated and completed design, to launch an international competitive tender for the implementation of the project. This approach entails migrating from the original FIDIC Yellow Book contract form (design and build) to the FIDIC Red Book contract form (construction only), thereby entrusting the works to a contractor specialized in execution on the basis of a certified design.

This migration to the Red Book represents the most secure and expeditious path to completing this project, while ensuring full compliance with lender requirements, preserving the entirety of the mobilized financing, and adhering to implementation deadlines.

We remain at your full disposal for any additional information and would be grateful for your decisions at the earliest convenience.

Please accept, Your Honorables Ministers, the assurances of our highest considerations.

Dr Asaph KABAASHA

Chief Executive Officer

WASAC Group Ltd.