WASAC GROUP LTD.

Office of the Chief Executive Officer

Kigali, 3 June 2026

To

His Excellency the Minister of Infrastructure

Ministry of Infrastructure (MININFRA)

Kigali

Subject: Request for Authorization to Recruit an Accredited Consultant and Migrate to FIDIC Red Book — KCSS Project

Your Excellency,

The Kigali Centralized Sewerage System (KCSS) — Contract No. 11.07.053/3707/W/ICB/22-23/PROC-WASAC-CEO/GU/es — is Rwanda's first centralized sewerage infrastructure at scale. This strategic project, valued at USD 63.9 million, is financed by the European Investment Bank (EIB — EUR 45 million) and the African Development Bank (AfDB — USD 31.9 million). It was awarded to CRCEG (China Railway Construction Engineering Group Co. Ltd), with CES Consulting Engineers serving as the supervision consultant. To date, the design has reached 90.2% completion; however, this was achieved after a cumulative delay of more than 27 months against an initial contractual design period of 6 months. Given the contractor's persistent failures — including failure to mobilize qualified staff, poor quality of deliverables, and inability to fulfil contractual obligations — WASAC Group formally notified the termination of the contract with CRCEG on 8 May 2026.

Following this termination, WASAC Group must take urgent action to safeguard the available financing, whose disbursement deadlines are set at 28 December 2027 for the EIB and 30 June 2028 for the AfDB.

It is also important to note that this proposed approach was discussed with the African Development Bank team during their last supervision mission and received a favourable assessment. The AfDB found the approach consistent with the financing timeline constraints and well-suited to the current stage of project design.

In this context, WASAC Group respectfully requests Your Excellency's authorization to proceed with the following two-step approach:

First, to recruit a consultant accredited by the Ministry of Infrastructure (MININFRA) to review and validate the existing design (90.2% complete) and finalize the remaining 10%. This step is essential to obtain a certified and complete design package that will serve as the basis for the works tender.

Second, on the basis of the validated and completed design, to launch an international competitive tender for the implementation of the project. This approach entails migrating from the original Yellow Book FIDIC contract form (design and build) to the Red Book FIDIC contract form (construction only), thereby entrusting the works to a contractor specialized in execution on the basis of a certified design.

This migration to the Red Book represents the most secure and expeditious path to completing this nationally significant project, while ensuring full compliance with lender requirements and adherence to implementation deadlines.

We remain at your full disposal for any additional information or working meeting you may deem appropriate, and would be grateful for your decision at the earliest convenience.

Please accept, Your Excellency, the assurances of our highest consideration.

Dr Asaph KABAASHA

Chief Executive Officer

WASAC Group Ltd.